## anonymous
ID | Project | Reporter | Assigned To | Priority | Severity | Reproducibility | Product Version | Projection | Date Submitted | ETA | OS | OS Version | Platform | View Status | Updated | Summary | Status | Resolution | Fixed in Version
40 | Blender3D | pegasossigi2 | Yomgui | normal | tweak | always | 2.50alpha0-test | none | 2010-01-28 | none |  |  |  | public | 2010-02-11 | No Material-preview | resolved | fixed | 2.50alpha0-test
43 | Blender3D | Yomgui | Yomgui | normal | minor | always | 2.50alpha0-test | none | 2010-02-08 | none | MorphOS | (all) | (all) | public | 2010-02-08 | loop cut doesn't handle 2 cuts only | resolved | fixed | 2.50alpha0-test
42 | Python | Yomgui | Yomgui | normal | minor | always | 3.1.1-head | none | 2010-02-07 | none | MorphOS | (all) | (all) | public | 2010-02-07 | PyRun_File() doesn't work | assigned | open
33 | Blender3D | pegasossigi2 | Yomgui | low | minor | always | 2.50alpha0-test | none | 2010-01-28 | none |  |  |  | public | 2010-02-07 | Presets not work | resolved | fixed | 2.50alpha0-test
37 | Blender3D | pegasossigi2 | Yomgui | normal | crash | always | 2.50alpha0-test | none | 2010-01-28 | none |  |  |  | public | 2010-02-04 | Sculp-Mode hangs the window | resolved | suspended
31 | Blender3D | Yomgui | Yomgui | normal | major | always | 2.50alpha0-test | none | 2010-01-26 | none | MorphOS | 2.x | (all) | public | 2010-02-04 | Bad display of text in UI | resolved | fixed | 2.50alpha0-test
41 | Python | Yomgui | Yomgui | high | tweak | always | 3.1.1-head | none | 2010-01-28 | none | MorphOS | (all) | (all) | public | 2010-01-28 | Python exception in Blender log at startup | resolved | fixed | 3.1.1-head
39 | Blender3D | pegasossigi2 | Yomgui | normal | major | always | 2.50alpha0-test | none | 2010-01-28 | none |  |  |  | public | 2010-01-28 | the ffmpeg export produce only black frames | acknowledged | open
35 | Blender3D | pegasossigi2 | Yomgui | low | major | always | 2.50alpha0-test | none | 2010-01-28 | none |  |  |  | public | 2010-01-28 | loading of sound in the videosequenceeditor is not possible | acknowledged | open
30 | Blender3D | pegasossigi2 | Yomgui | low | minor | always | 2.50alpha0-test | minor fix | 2010-01-26 | 2-3 days |  |  |  | public | 2010-01-26 | No tiff export | confirmed | open
22 | Python | Yomgui | Yomgui | high | major | always | 2.5.4-r39 | none | 2009-11-11 | none | MorphOS | (all) | (all) | public | 2009-12-08 | PROGDIR: seems to be not set, unable to load python.library in a local libs dir so | assigned | open
24 | Python | Yomgui | Yomgui | high | major | always | 2.5.4-r39 | minor fix | 2009-12-07 | 2-3 days | MorphOS | (all) | (all) | public | 2009-12-08 | sys.platform not correct for MorphOS. | assigned | open
7 | Blender3D | Yomgui | Yomgui | normal | feature | always | 2.46 | none | 2008-06-18 | none |  |  |  | public | 2008-07-08 | Clipboard support (GHOST) | assigned | open
10 | Blender3D | Yomgui |  | normal | crash | always | 2.46 | none | 2008-06-24 | none | MophOS | All | Pegasos (all) | public | 2008-06-24 | Crashes when loading .blend file with absolute directory path inside. | new | open